## Sheet1
Component | Requirement | Description | Work Estimate w/u | Priority
pre-/post- processing service | Configuration | The service must read from the configuration file its options including the information (per language) about the available text pre-/post-processing scripts. | 8 | M
| Console | The service must provide a console for monitoring the run-time status and change run-time parameters. | 8 | M | MoSCoW model
| Core | The service must provide a JSON, via WebSockets, service allowing to receive and reply to two types of requests: Pre-processing and Post-processing. | 8 | M | M - Must | First priprity, that is absolutely necessary to deliver
|  | It must be possible for the server to store the input/output text files in specified folder(s). |  | M
|  | On the server, the text for processing is to be stored in a file and the resulting text is to be read from a file. | 8 | M
|  | The service is to be able to give an id for the pre-processing request's source information and to send it back to the client with the pre-processed text result and the source language. | 8 | M
|  | The source id information is to be communicated to the server from the client with the post-processing request. | 2 | M
|  | The application is to be multi-threaded for speed efficiency. Handle multiple requests simultaneously. | 8 | M
|  | The application is to be configurable for the maximum number of files descriptors to work with. Can be limited on the level of the number of worker threads | 6 | S
| Pre-process | The pre-processing request must contain: source text data, and the source language | 4 | M | S - Should | Second priority, that is to be delivered, but can be omitted in case of lack of time
|  | The language is to be possible to be detected by the pre-processing script. In this case the source language is set to <auto> | 4 | S
|  | The pre-processor response must contain the resulting text, the (detected) source language, and the source set unique identifier. | 8 | M
|  | If the source language detection was needed but could not be performed (the language could not be detected) an error is reported. | 4 | M
|  | If the requested source language (not <auto>) is not known then a default pre-processor must be used | 8 | S
|  | If the requested source language (not <auto>) is not known and there is no default pre-processor then an error is to be reported. | 4 | M
| Post-process request | The post-processing request must contain: target text data, the target language, and the unique identifier of the source set. | 4 | M | C - Could | Third priority, that is desired to be delivered, in case there is time left for it
|  | The post-processor response must contain the resulting target text | 8 | M
|  | The target language must be given, can not be auto detected | 0 | M
|  | If the requested target language is not known then a default post-processor must be used | 8 | S
|  | If the requested target language is not known and there is no default post-processor then an error is to be reported. | 4 | M | W - Would | Fourth priority, that is desired but is definitely not for the delivery
Web client | Pre-proc. server | It should be possible to provide/enable/disable the pre-procesing service address | 8 | M
| Post-proc. server | It should be possible to give/enable/disable the post-procesing service address | 8 | M
| Progress | The pre and post processing progress is to be shown in the progress bar | 8 | S
| Pre-process | The client must split the source text, and send it for pre-processing to the eserver and process the response. | 8 | M
| Post-Process | The client must split the target text, and send it for post-processing to the eserver and process the response. | 8 | M
Console client | Pre-proc. server | It should be possible to give the pre-procesing service address and port in the command line | 8 | M
| Post-proc. server | It should be possible to give the post-procesing service address and port in the command line | 8 | M
| Progress | The progress on pre- and post- processing is to be reported via info messages. | 8 | S
| Pre-process | The client must split the source text, and send it for pre-processing to the server and process the response. | 8 | M
| Post-Process | The client must split the target text, and send it for post-processing to the server and process the response. | 8 | M