## Sheet1
Requirement | Description | Work Estimate w/u | Priority
Basic text input | The interface should posess the possibility to take a text from the input text area (as is) and send it to the translation service. | 16 | M | MoSCoW model
Basic text file | The interface should posess the possibility to take a text from the file on a disk (as is) and send it to the translation service. | 32 | M | M - Must | First priprity, that is absolutely necessary to deliver
Text pre-processing | The source text is to be send to a websocket server for lower casing, tokenization and one-sentence-per line splitting. This is to be done before the text is send to translation. | 40 | S | S - Should | Second priority, that is to be delivered, but can be omitted in case of lack of time
Text post-processing | The target text is to be send to a websocket server for begin restored to its original shape. This is to be done after the text is translated. | 40 | S | C - Could | Third priority, that is desired to be delivered, in case there is time left for it
Language dertection | The source language is to be detected automatically | ? | W | W - Would | Fourth priority, that is desired but is definitely not for the delivery
Instant translate | As the sentence is being typed the translations are requested and displayed as we type | 16 | W
Multiple source/target | Multiple source and target languages must be supported for choosing. | 16 | S
Source/target loading | The available source to target language pairs are to be loaded from the server | 24 | S
Translation info | Allows to requrest and display translation info per sentence, e.g. stack capacities | 40 | C
Translation status | Proper visualization of translation status per sentence, cancelled, error etc | 16 | C