## Sheet1
Requirement | Description | Work Estimate w/u | Priority
Request language pairs Decoder | The decoder interface is to be extended with a possibility to request available source-target translation pairs | 16 | S
Check language pairs Decoder | When a translation request message is received by the decoder it must check that the source and target language pairs are the same as in the decoder's server configuration file | 8 | M | MoSCoW model
Translation priorities Decoder | Introduce message priorities. Each message must have a requested priority indicator. The priority is to be used by the decoding server. There should be several message queues introduced for various priorities. Even a low-priority queues must have worker threads associated with them at all times. The mode load there is on the priority queues the more workes shall be dedicated to work on them. | 40 | C | M - Must | First priprity, that is absolutely necessary to deliver
Load Ballancer | The load ballancer must load the list of available online translation services, request them for the supported source-targer translation pairs and then forward the translation request to the appropriate servers with some basicdistribution strategy. The received responces are to be sent back to the clients. | 40 | M | S - Should | Second priority, that is to be delivered, but can be omitted in case of lack of time
Extended Load Ballancer | A smarter load ballancer strategy is to be introduced, for example one shall track the amount of translations requested per translation server, so that the requests are evenly distributed. | 16 | S | C - Could | Third priority, that is desired to be delivered, in case there is time left for it
Request language pairs Ballancer | The load ballancer must suppot s request of the supported source-target language pairs | 16 | S | W - Would | Fourth priority, that is desired but is definitely not for the delivery
Check language pairs Ballancer | The load ballencer must check on the source and target translations in the translation request and report an error if there is no server that can provide such a translation | 8 | M
Re-connection to Decoders | In case of a connection drop between the ballancer and the decoding servers the connection is to be restored by re-connecting. The latter is to be done periodically by a separate re-connect thread that tries to re-establish the server connecitons. | 24 | C